Procurement Journey

Contract Variation Workflow Diagram

Change Identified

- Need Arises (operational, legislative, performance, etc)

- Contract Manager logs change

Initial Assessment

- Is the variation necessary

- Is the change within contract scope and budget?

- Initial risk categorisation

Procurement & Legal Review

- Confirm variation is not a substantial modification

- Confirm compliant route

- Validate change control steps

Impact Assessment

- Commercial Impact

- Legal Regulatory Compliance

- Financial Impact

- Service, KPI, risk impacts

- Market Comparison (if needed)

Draft Variation Agreement

- Changes Control Notice (CCN)

- Update schedules/KPIs

- Revised pricing

- Implementation plan

Supplier Engagement

- Discuss proposed change

- Supplier impact assessment

- Seek price/time proposals

- Negotiate changes

Final Approval & Sign-off

- Authority signature

- Supplier signature

- Store in contract file

Internal Approvals

- SRO Approvals

- Finance approval (if cost)

- Governance board approval (for high-risk changes)

Implementation & Comms

- Notify stakeholders

- Update processes & systems

- Supplier implements change

Update Registers & Publish

- Update variation log

- Update contract register

- Publish Contract Modification Notice (if legally required)

Review & Assurance

- Ensure change is embedded

- Monitor performance/KPIs

- Audit trail maintained