Procurement Journey

Lessons Learned Template – Populated Examples

Below are two example completed one-page lessons learned templates. They are fictional but realistic and designed for guidance and training purposes within the Scottish public sector.

They show the appropriate level of detail for medium/high-value, medium/high-risk contracts and demonstrate what “good” looks like.  Although it is expected that for complex / long running contracts there would be more positive and negative points available for you to record.

Example 1 – Facilities Management Services Contract

Lessons Learned Summary

Contract Overview

- Contract Title: Facilities Management Services (Multi-Site)

- Supplier Name: ABC Facilities Ltd

- Organisation / Directorate: Estates & Facilities

- Contract Manager: J. McLeod

- Contract Value (approx.): £1.8m

- Contract Period: April 2021 – March 2024

- Stage Reviewed: ☑ Closure

Purpose of Review

End-of-contract review to inform re-procurement of facilities management services and identify improvements for future contract management.

What Worked Well

| What worked well | Why it worked |
| --- | --- |
| Clear performance KPIs | KPIs were measurable and linked to service outcomes |
| Regular monthly review meetings | Issues were identified early and addressed promptly |
| Single point of contact | Improved communication and accountability |

What Did Not Work as Intended

| Issue / challenge | Cause (high level) | Impact |
| --- | --- | --- |
| Slow response to urgent repairs in Year 1 | Mobilisation underestimated staffing levels | Service disruption and complaints |
| Inconsistent reporting quality | Reporting requirements not clearly specified | Additional management time required |

Key Lessons Learned

| Lesson learned | Applies to |
| --- | --- |
| Mobilisation plans must be reviewed and stress-tested before contract start | Mobilisation |
| Reporting requirements should be clearly defined in the contract | Procurement / Contract management |

Improvement Actions

| Action | Owner | Timescale |
| --- | --- | --- |
| Strengthen mobilisation requirements in future tenders | Procurement | Next procurement |
| Introduce standard reporting templates | Contract Management | Within 3 months |

Sharing and Use of Learning

- Who should see this learning?
☑ Contract team ☑ Procurement / Commercial

- How will this be used?
☑ Inform future procurements
☑ Update templates / guidance

Review Sign-Off

- Completed by: J. McLeod

- Date: 15 April 2024

- Reviewed / Approved by: Not required

Example 2 – Digital Support Services Contract

Lessons Learned Summary

Contract Overview

- Contract Title: ICT Application Support Services

- Supplier Name: Digital Solutions Scotland Ltd

- Organisation / Directorate: Digital & IT Services

- Contract Manager: S. Ahmed

- Contract Value (approx.): £950k

- Contract Period: January 2022 – December 2024

- Stage Reviewed: ☑ In-life (Annual Review)

Purpose of Review

Annual review following recurring service performance issues to identify improvements and inform contract extension decision.

What Worked Well

| What worked well | Why it worked |
| --- | --- |
| Collaborative working relationship | Open and constructive engagement |
| Flexible approach to minor changes | Avoided unnecessary formal variations |

What Did Not Work as Intended

| Issue / challenge | Cause (high level) | Impact |
| --- | --- | --- |
| Missed service levels during peak periods | Demand higher than forecast | Reduced user satisfaction |
| Escalation process unclear | Governance not fully documented | Delayed issue resolution |

Key Lessons Learned

| Lesson learned | Applies to |
| --- | --- |
| Demand assumptions should be reviewed annually | Contract management |
| Escalation routes must be clearly documented | Governance |

Improvement Actions

| Action | Owner | Timescale |
| --- | --- | --- |
| Update escalation and governance documentation | Contract Manager | 1 month |
| Review demand forecasts with supplier | Contract Manager | Before extension decision |

Sharing and Use of Learning

- Who should see this learning?
☑ Contract team ☑ Procurement / Commercial

- How will this be used?
☑ Inform extension decision
☑ Improve in-life contract management

Review Sign-Off

- Completed by: S. Ahmed

- Date: 10 January 2025

- Reviewed / Approved by: Service Manager

Bottom of Form