## Task_Table
Project Name : |  |  |  |  | Project Ref :
ID | Task | Duration (days) | Start date | Current Status | Finish date | Approval review and sign-off Points | Comments
A | Develop Strategy |  | 2015-12-12 |  |  | Project Initiation
1 | Establish UIG
2 | Identify Stakeholders
3 | Profile the Commodity/Service
4 | Identify Contract Status & Conduct Spend Analysis
5 | Consider Sustainability Aspects
6 | Profile the Commodity/Service
7 | Analyse Supply Market
8 | Shape the Requirement
9 | Identify Initial Opportunities |  |  |  |  | Review and sign-off opportunities
10 | Develop Commodity/Service Strategy
11 | Determine Procurement Route
12 | Produce Executive Summary |  |  |  |  | Approve Strategy and ensure budget is available
B | Develop Documents
13 | Produce Specification
14 | Consider Selection and Award Criteria
15 | ESPD (if applicable)
16 | Invitation to Tender (ITT)
17 | Contract Notice |  |  |  |  | Sign-off documents
C | Supplier Selection
18 | Publicise the Contract
19 | Issue ESPD (if applicable)
20 | Assess Responses
23 | Identify suppliers to be invited to tender and notify all suppliers of outcome
D | Issue ITT
24 | Issue ITT
25 | Hold Supplier (Bidders) Meeting
26 | Respond to Suppliers Questions
E | Open & Evaluate Tender
27 | Deadline for Tender Submissions
28 | Open Tenders
29 | Conduct Technical Evaluation
30 | Conduct Price Evaluation
31 | Hold Presentation/Site Visits (if applicable)
32 | Combine Price/Quality Evaluations
F | Post Tender Clarification
33 | Tender Clarification (if applicable)
G | Contract Award |  |  |  |  | Obtain approval prior to issuing notification
34 | Notify suppliers of Contract Award Decision
35 | Observe the Standstill period (if applicable)
36 | Award the Contract
H | Contract Implementation |  |  |  |  | Obtain approval prior to commencing with implementation
37 | Communicate Details of Contract/Framework Agreement
38 | Meet with Successful Supplier(s)
39 | Review Content Management Requirements
40 | Produce Supplier/Buyer Guides
41 | Hold Supplier/Buyer Events
I | Contract and Supplier Management
42 | Formalise Process
43 | Collate and Review Performance Management Information
44 | Hold Performance Review Meetings
45 | Ensure Robust Exit Strategy has been agreed
Key
In Progress
Planned
Not Yet Agreed
Ref: AR-7-B
date: 23/03/17
Note on E2: z608474: See 'Key' below