## Status
Commodity/Service Plan | Commodity/Service X |  | Commodity/Service Y |  | Commodity/Service Z
| Date of milestone/ % complete on task | Comments | Date of milestone/ % complete on task | Comments | Date of milestone/ % complete on task | Comments
PLAN
Initiate Plans and Engage Full Team | % complete |  | % complete |  | % complete
Identify Stake-holders | % complete |  | % complete |  | % complete
Issue Data Request & chase information | % complete |  | % complete |  | % complete
Analyse Data | % complete |  | % complete |  | % complete
Collate existing commodity/service knowledge | % complete |  | % complete |  | % complete
Create commodity/service demand profile | % complete |  | % complete |  | % complete
Collate user requirements | % complete |  | % complete |  | % complete
Complete market analysis | % complete |  | % complete |  | % complete
Complete cost driver analysis | % complete |  | % complete |  | % complete
Hold opportunity workshop | % complete |  | % complete |  | % complete
Formulate specification | % complete |  | % complete
Update strategy (including benefit case and implementation plan) | % complete |  | % complete |  | % complete
Obtain senior stakeholder endorsement | % complete |  | % complete |  | % complete
Sign Off from WorkStream Lead and Comm Sponsor | DATE REQD |  | DATE REQD |  | DATE REQD
TENDER PROCESS [RFI & RFP]
Identify Key Suppliers (Pre-Qualification/Pre-tender) | % complete |  | % complete |  | % complete
Collate Evaluation Criteria | % complete |  | % complete |  | % complete
Validate Evaluation Criteria | % complete |  | % complete |  | % complete
Prepare Tender Package | % complete |  | % complete |  | % complete
Validate pricing structure and tender document | % complete |  | % complete |  | % complete
Work Stream lead to Sign off Tender Package | % complete |  | % complete |  | % complete
Issue Tender Package | DATE REQD |  | DATE REQD |  | DATE REQD
Respond to Supplier Enquiries (Circular Advice Note) | % complete |  | % complete |  | % complete
Evaluate Tender Response | % complete |  | % complete |  | % complete
Present Initial Recommendations | % complete |  | % complete |  | % complete
Product Sampling | % complete |  | % complete |  | % complete
Clarify / Negotiate with Preferred Suppliers | % complete |  | % complete |  | % complete
AWARD Contract
Approval of Recommendation | % complete |  | % complete |  | % complete
Award Contract subject to holding period | DATE REQD |  | DATE REQD |  | DATE REQD
Post-Tender Debriefs | % complete |  | % complete |  | % complete
IMPLEMENTATION
Compile Implementation Instructions for end users | % complete |  | % complete |  | % complete
Write Supplier Management Plan | % complete |  | % complete |  | % complete
Write Contract Management Plan | % complete |  | % complete |  | % complete
Write Compliance Management Plan | % complete |  | % complete |  | % complete
Supplier to create catalogue (if not included as part of tender) to be removed | % complete |  | % complete |  | % complete
Buyer to issue to Supplier Adoption team for validation (should remove supplier training material) | % complete |  | % complete |  | % complete
Buyer to QA Catalogue Content - Technical and Commercial details | % complete |  | % complete |  | % complete
Create and Load Catalogue on to eProcurement System | % complete |  | % complete |  | % complete
Catalogue publication | % complete |  | % complete |  | % complete
Commodity/Service Available for Use | DATE REQD |  | DATE REQD |  | DATE REQD
Facilitate Adoption and Compliance | % complete |  | % complete |  | % complete
REVIEW
Collate Lessons Learnt / Communicate | % complete |  | % complete |  | % complete
Commodity/Service Complete | DATE REQD |  | DATE REQD |  | DATE REQD
Reference: AR-5-B
Released: 23/03/17

## Risks
Risks
Ref | Date | Identified by | Risk Owner | Commodity | Description | Probable Costs £ | Action? | When? | Who? | Impact (1-3) | Probability (1-3) | Severity Score | Stream | Status | Date Closed
Note on A3: SMCARDLE: Please use following nomenclature 1.Each workstream has a dedicated letter, S- Sourcing E- eProcurement K- KPI's O- Org design & Recruitment P- People Development C- Comms and change management L- Logistics. 2. The second letter is either an R for Risks or an I for Issue. 3. Number - please use 0 in front of the first nine numbers as it allows filtering in numerical order.
Note on B3: SMCARDLE: Date risk was raised.
Note on C3: SMCARDLE: Name of person who has raised the risk.
Note on D3: Name of person who owns the risk. It is the responsibility of the Workstream Leader to assign the owner.
Note on E3: Name of Commodity affected. Also use all or none as appropriate. Mostly used by Sourcing but if it's in all registers makes it easier to combine them at a later stage where approval of mitigating actions is required
Note on F3: This should be a detailed description of the risk. Try to be punchy and to the point.
Note on H3: List actions numerically within the cell which will mitigate the risk.
Note on I3: For each action assign an target end date and an owner using initials. Again in numerical order aligned with the numbered list in the actions field.
Note on K3: Assess the impact of the Risk on a scale of 1-3, with a 3 denoting a high impact and 1 denoting a low impact. Please assess the impact harshly as people have a tendency to over state the impact. The impact rating is dynamic and may change over time as you review the risk.
Note on L3: Assess the likely hood of the risk occurring on a scale of 1-3, with a 3 denoting a high likely hood that it will occur and a 1 denoting a low likely hood. The probability rating is dynamic and may change over time as you review the risk.
Note on M3: This is calculated by Impact X Probability and is used to rank risks.
Note on O3: When a risk is entered it starts life as Open. Once completly mitigated so that it is no longer a risk or the risk goes away then it changes to Closed. When a risk is closed enter the date on which it was closed. Risks may also occasionally be placed on Hold. A risk may also change to an issue. If this is the case then change the status to Occured and copy across the risk to the issue register and progress.
Note on P3: Enter the date the risk was closed in the format dd/mm/yy.

## Issues
Issues
Ref | Date | Identified by | Issue Owner | Commodity | Description | Probable Costs £ | Action? | When? | Who? | Impact (1-3) | Probability (1-3) | Severity Score | Stream | Status | Date Closed
Note on A3: SMCARDLE: Please use following nomenclature 1.Each workstream has a dedicated letter, S- Sourcing E- eProcurement K- KPI's O- Org design & Recruitment P- People Development C- Comms and change management L- Logistics. 2. The second letter is either an R for Risks or an I for Issue. 3. Number - please use 0 in front of the first nine numbers as it allows filtering in numerical order.
Note on B3: Date issue was raised.
Note on C3: Name of person who has raised the issue.
Note on D3: Name of person who owns the issue. This is the responsibility of the Workstream Leader to assign the owner.
Note on E3: Name of Commodity affected. Also use all or none as appropriate. Mostly used by Sourcing but if it's in all registers makes it easier to combine them at a later stage where approval of mitigating actions is required
Note on F3: This should be a detailed description of the issue Try to be punchy and to the point.
Note on H3: List actions numerically within the cell which will mitigate the risk.
Note on I3: For each action assign an target end date and an owner using initials. Again in numerical order aligned with the numbered list in the actions field.
Note on K3: Assess the impact of the issue on a scale of 1-3, with a 3 denoting a high impact and 1 denoting a low impact. Please assess the impact harshly as people have a tendency to over state impact. The impact rating is dynamic and may change over time as you review the issue.
Note on L3: Assess the likely hood of the issue occurring on a scale of 1-3, with a 3 denoting a high likely hood that it will occur and a 1 denoting a low likely hood. The probability rating is dynamic and may change over time as you review the issue.
Note on M3: This is calculated by Impact X Probability and is used to rank issues.
Note on O3: When an Issue is entered it starts life as Open. Once completly mitigated it changes to Closed. When an issue is closed enter the date on which it was closed.
Note on P3: Enter the date the issue was closed in the format dd/mm/yy.