## Sheet1
Procurement Journey
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
SRO – Senior Responsible Owner / Contract Owner | Activity / Responsibility | SRO | CM | PT | SL | FIN | R&A/LEG | SRM | SU | SUP
CM – Contract Manager (day-to-day lead) | Develop & maintain Contract Management Plan | A | R | C | C | C | C | C | C | C
PT – Procurement/Commercial Team | Set KPIs, SLAs & Balanced Scorecard | A | R | C | C | C | C | C | C | I
SL – Service/Technical Lead | Monthly performance monitoring | I | R | C | R | C | I | C | C | R
FIN – Finance Lead | Quarterly performance review | A | R | C | C | C | C | R | I | R
R&A/LEG – Risk, Assurance & Legal | Annual strategic review | A | R | C | C | C | C | R | I | R
SRM – Strategic Supplier Relationship Manager (if applicable) | Approve contract variations | A | R | C | C | C | R | C | I | R
SU – Contract Users / Operational Stakeholders | Manage day-to-day supplier relationship | I | R | C | C | I | I | C | C | R
SUP – Supplier-side Contract Manager | Strategic relationship management | A | C | C | I | I | I | R | I | R
| Risk register ownership & updates | A | R | C | C | C | C | C | I | C
| Issue/incident management | I | R | C | R | C | C | I | I | R
| Financial monitoring & invoice approval | I | C | I | I | R | I | I | I | R
| Audit compliance & evidence | A | R | C | C | C | R | I | I | R
| Change control management | A | R | C | C | C | R | C | I | R
| Business continuity & disaster recovery assurance | A | R | C | R | C | R | I | I | R
| Stakeholder communication | A | R | C | C | I | I | C | R | I
| Re-tendering & exit planning | A | R | R | C | C | C | C | I | C
| Contract close-out activities | A | R | C | C | C | C | C | I | R